## Test Scenerio
Project Name |  | Daraz Shopping App | Test Case Start Date | 14/11/2023 | Test Execution Start Date | - -
Module Name |  |  | Test Case End Date | 14/11/2023 | Test Execution End Date | - -
Epic |  |  | Test Case Developed By | Noor E Arafin Rafi | Browser (tested) | Yes
Developer Name (Test Lead) |  |  | Test Case Reviewed By |  | Performance (tested) | No
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases | Number of Sucessful TestCase |  | Number of Failed TestCase | Out of scope | Not Executed
TS_R001 (Login) |  | Verify the working of Login Functionality | P1 | 25 | 22 |  | 3 | 0 | 0 |  | Progress Tracker
TS_R002 (Signup) |  | Verifty the working of Signup Functionality | P2 | 10 | 10 |  | 0 |  | 0 |  | Date | Number Of Test Case
TS_R003 (Account Information) |  | Verifty the working of Account Information Functionality | P3 | 13 | 11 |  | 2 |  | 0 | 250 | 18 / 10 / 23 | 101
TS_R004 (Search) |  | Verify the working of Search Functionality | P2 | 12 | 12 |  | 0 |  | 0 |  | 19 / 10 / 23 | 125
TS_R005 (Add to Cart) |  | Verify the working of 'Add to Cart' Functionality | P2 | 15 | 15 |  | 0 |  | 0 |  | 22 / 10 / 23 | 155
TS_R006 (Home Page) |  | Verify the working of Home Page Functionality | P2 | 19 | 18 |  | 1 |  | 0 |  | 23 / 10 / 23 | 189
TS_R007 (Check out) |  | Verify the working of Check Out Functionality | P1 | 22 | 20 |  | 2 |  | 0 |  | 24 / 10 / 23 | 224
TS_R008 (Account) |  | Verify the working of Account Functionality | P3 | 18 | 17 |  | 1 |  | 0 |  | 25 / 10 / 23 | 250
TS_R009 (My Orders) |  | Verify the working of My Order Functionality | P2 | 11 | 13 |  | 0 |  | 0 |  | 26 / 10 / 23 | 260
TS_R010 (Payment Method) |  | Verify the working of Payment Method Functionality | P1 | 11 | 10 |  | 1 |  | 0
TS_R011 (My Return) |  | Verify the working of My Returns Method Functionality |  | 10 | 10 |  | 0 |  | 0
TS_R012 (Daraz live) |  | Verify the working of Daraz Live Functionality |  | 4 | 3 |  | 1 |  | 0
TS_R012 (Search Filter) |  | Verify the working of Search Filter Functionality |  | 19 | 19 |  | 0 |  | 0
TS_R012 (Product Page) |  | Verify the working of Product Page Functionality |  | 25 | 25 |  | 0 |  | 0
TS_R012 (Cart) |  | Verify the working of Cart Page Functionality |  | 10 | 10 |  | 0 |  | 0
TS_R013 (Messages) |  | Verify the working of Messages Page Functionality |  | 18 | 18 |  | 0 |  | 0
TS_R014 (Discover) |  | Verify the working of Discover Page Functionality |  | 8 | 8 |  | 0 |  | 0
TS_R015 (Wishlist) |  | Verify the working of Wishlist Functionality |  | 10 | 10 |  | 0 |  | 0
[5 empty] | 251 |  | 11 | 0 | 0

## Test Summery Report
Test Case Report
Project Name | Daraz Online Shopping App
Module Name | Check Out From (Test Scenerio)
Feature Name
Test Case Version
Executed By | Noor E Arafin Rafi
Written by | Noor E Arafin Rafi
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out of Scope | Total Test Cases
Test Case | 251 | 11 | 0 | 0 | 262

## Login
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCL_001 | (TS_R001) Login Functionality | Checking the "Login/Signup" Button | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button | None | Should clickable the "Login/Signup" button | Found as per the expectation | P1 | PASS
TCL_002 | (TS_R001) Login Functionality | Verify the Login screen has the necessary fields & elements | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Checking all necessary field & elements | None | Should be present every mandatory fields | Found as per the expectation | P1 | PASS
TCL_003 | (TS_R001) Login Functionality | Checking that weather the displayed fields & elements are aligned in the right form | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Checking aligned in the right form | None | Should be aligned in the expected form as per the requirement | Found as per the expectation | P1 | PASS
TCL_004 | (TS_R001) Login Functionality | Checking the UI of different elements, sizes, and colors | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Checking element size colours | None | Should be matched with the expected form as per the requirement | Found as per the expectation | P1 | PASS
TCL_005 | (TS_R001) Login Functionality | Verify whether the login screen is responsive | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Split the screen | None | The screen should be split in the phone | Found not as per the expectation | P1 | FAIL | BUG SS_split_unable
TCL_006 | (TS_R001) Login Functionality | Verify Login field with phone number | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter signed phone number in phone number field | 1628942091 | Should open new screen for enter password | Found as per the expectation | P1 | PASS
TCL_007 | (TS_R001) Login Functionality | Verify Login field with wrong and short length phone number | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter wrong length phone number | 148482434 | Should not open new screen for enter password & show error message below the next field | Found as per the expectation | P1 | PASS
TCL_008 | (TS_R001) Login Functionality | Verify whether Login with phone number field take any alphabet | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Try to enter any alphabet | None | The phone should not allow to take any alphabet in the field | Found as per the expectation | P1 | PASS
TCL_009 | (TS_R001) Login Functionality | Verify Login with phone number field with not signed valid phone number | "1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter Valid not signed phone number | 1816960476 | Should send OTP in the phone and request user to sign up | Found as per the expectation | P1 | PASS
TCL_010 | (TS_R001) Login Functionality | Verify the title of the login screen | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Check title on the login screen | None | Should be as per the requirement | Found as per the expectation | P1 | PASS
TCL_011 | (TS_R001) Login Functionality | Verify whether there is a check box with the label of "Remember Password" on the login screen or not | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter signed phone number 4.Check "Remember Me" Checkbox | None | when login to the website there should be a "Remember me " check box | Found not as per the requirement | P1 | FAIL | Missing Checkbox
TCL_012 | (TS_R001) Login Functionality | Verify that the user will be able to Login with their account with the current credential | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter signed phone number and password 5.Press Login button | None | User should able to Login with correct credential | Found as per the expectation | P1 | PASS
TCL_013 | (TS_R001) Login Functionality | Verify that the Password entered should be in encrypted form | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Enter signed phone number 5.Enter Password | ******** | The Password entered should be in encrypted form | Found as per the expectation | P1 | PASS
TCL_014 | (TS_R001) Login Functionality | Verify that an "eye" icon is added to the password field or not | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Enter signed phone number 5. Check eye button | None | should be there an "eye" icon | Found as per the expectation | P1 | PASS | B3:B27
TCL_015 | (TS_R001) Login Functionality | Verify the error message should displayed after entering only phone number and leaving the Password field blank | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Enter signed phone number 5. Press "Login" button | None | Should display an error message | Found as per the expectation | P1 | PASS
TCL_016 | (TS_R001) Login Functionality | Verify the error message should displayed after entering only the Password and leaving the phone number field blank | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Enter signed phone number 5.Erase phone number 6. Press "Login" button | None | Should display an error message | Found as per the expectation | P1 | PASS
TCL_017 | (TS_R001) Login Functionality | verify the error message should be displayed after entering an invalid email format | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Click "Login with Email" 5.Enter invalid email 6. Press "Login" button | None | Error message should display if the email is invalid | Found as per the expectation | P1 | PASS
TCL_018 | (TS_R001) Login Functionality | Verify the displayed error message grammar should be correct | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Click "Login with Email" 5.Enter invalid email 6. Press "Login" button | None | The error message should be grammatically correct | Found as per the expectation |  | PASS
TCL_019 | (TS_R001) Login Functionality | Verify the error message should display after entering the invalid user credential before pressing login button | 1. Goto the Daraz App 2. Click on the "Account" button in the lower right corner 3.Click "Login/Signup" button 4.Click "Login with Email" 5.Enter invalid email 6.Enter password | enter an invalid password | An Error message should displayed if the user credential is invalid | Found not as per the expectation |  | FAIL | Invalid_credintial
TCL_020 | (TS_R001) Login Functionality | verify all the functionalities should be working conditions as the user sign-in from the social login | 1. Goto the URL https://evaly.com.bd/ 2. Click on the "Sign in" button in the right corner. 3. click on "Sign in with google" 4.click on "Sign in with facebook" | None | Should be logged in to the current page if the user uses the social login | Found as per the expectation |  | PASS
TCL_021 | (TS_R001) Login Functionality | Verify it should not be always in loading in case the user adds an invalid password and email/phone number | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Enter signed phone number 5.Enter invalid password | enter an invalid password | User should not be always in loading in case the user adds an invalid password and email | Found not as per the expectation |  | PASS
TCL_022 | (TS_R001) Login Functionality | verify while typing in the password field there will be display a "Forgot Password" link under the password field | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.check forget password link | None | Should display a "Forgot Password" link | Found as per the expectatioon |  | PASS
TCL_023 | (TS_R001) Login Functionality | Check there is an OTP input field for verify the email address or phone number | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.check forget password link 5.Enter Phone or Email | None | There Should be an OTP input field for email verification | Found as per the expextation |  | PASS
TCL_024 | (TS_R001) Login Functionality | Verify while clicking on the "Resend OTP" the timer starts again | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.check forget password link 5.Enter Phone or Email | None | The timer should starts again | Found as per the expectation |  | PASS
TCL_025 | (TS_R001) Login Functionality | Verify While Clicking on the "Resend OTP" a new OTP will send to the particular email address | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.check forget password link 5.Enter Phone or Email | None | The same OTP should not sent by the same email successively | Found as per the expectation |  | PASS

## Signup
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCS_001 | (TS_R002) Signup Functionality | Checking whether the Phone number field is responsive | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Click Enter Phone Number | None | Should be clickable and typeable also | Found as per the expectation |  | PASS
TCS_002 | (TS_R002) Signup Functionality | Checking OTP is Automatically field in screen | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Click Enter Phone Number 5.auto fillup OTP | None | Should auto paste OTP and redirect for give pass word and confirm password Field | Found as per the expectation |  | PASS
TCS_003 | (TS_R002) Signup Functionality | Checking Password and Confirm Password Field | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Click Enter Phone Number 5.auto fillup OTP 6.Check Password and Confirm Password | None | Should be clickable and typeable also | Found as per the expectation |  | PASS
TCS_004 | (TS_R002) Signup Functionality | Checking enter password and confirm password equality | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Click Enter Phone Number 5.auto fillup OTP 6.Enter Password and Confirm Password | None | Should display error message if two aren't same | Found as per the expectation |  | PASS
TCS_005 | (TS_R002) Signup Functionality | checking whether the "password" and "confirm password" field values are encrypted | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Click Enter Phone Number 5.auto fillup OTP 6.Enter Password and Confirm Password | None | Should be encrypted the values | Found as per the expectation |  | PASS
TCS_006 | (TS_R002) Signup Functionality | Verify all the fields in the Register Account page have the proper placeholders | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button 4.Check Proper Placeholder | None | Proper Placeholder texts should be displayed in these fields | Found as per the expectation |  | PASS
TCS_007 | (TS_R002) Signup Functionality | Verify the UI of the 'Signup page' | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button | None | Proper and good UI should be displayed on the 'Sign up' page | Found as per the expectation |  | PASS
TCS_008 | (TS_R002) Signup Functionality | Verify 'Sign Up' functionality in all the supported environments | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click ""Login/Signup"" button | None | Sign up' functionality should work in all the supported environments | Found as per the expectation |  | PASS

## Account Information
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCAF_001 | (TS_R003) Account Information Functionality | Check all clickable field in account information screen | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.check all clickable field | None | Should be workable | Found as per the expectation |  | PASS
TCAF_002 | (TS_R003) Account Information Functionality | Checking random alpahbet in field in Full name section | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.enter name | abhgdsfsdh | should give error message | Found not as per the expectation |  | FAIL | Random alphabet
TCAF_003 | (TS_R003) Account Information Functionality | checking special character in Full name field | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.enter name with special character | @9834r | Should not allow | Found as per the expectation |  | PASS
TCAF_004 | (TS_R003) Account Information Functionality | Checking "Birthday" field with recent birthdate | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.enter recent month or date as a birthdate | 14/10/2023 12/7/2023 | Should not allow current month or year as a birthdate | Found not as per the expectation |  | FAIL | Bug for unreal Birthdate
TCAF_005 | (TS_R003) Account Information Functionality | Checking "Birthday" field with future birthdate | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.enter future month or date as a birthdate | 2023-12-12 | Should display an error message | Found as per the expectation |  | PASS
TCAF_006 | (TS_R003) Account Information Functionality | Checking grammatical mistake or spelling mistake in account information screen | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.Checking grammatical and spelling mistake | None | should not any grammatical mistake | Found as per the expectation |  | PASS
TCAF_007 | (TS_R003) Account Information Functionality | Checking add mobile functionality | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.add phone 6.check all activity include verification | 1628942091 | Should able to add phone number | Found as per the expectation |  | PASS
TCAF_008 | (TS_R003) Account Information Functionality | Checking change email functionality | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.Change email | .harry@gmail.com | Should able to change email | Found as per the expectation |  | PASS
TCAF_009 | (TS_R003) Account Information Functionality | Checking Gender Functionality | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.complite login 4.Click "setting" button at right upper corner 5.Check gender dropdown | None | Should be accessible | Found as per the expectation |  | PASS
TCAF_010 | (TS_R003) Account Information Functionality | Verify the UI of the '' page | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click "setting" button at right upper corner 4.Click 'Account Information' page | None | Proper and good UI should be displayed on the 'Account Information' page | Found as per the expectation |  | PASS
TCAF_011 | (TS_R003) Account Information Functionality | Verify 'Sign Up' functionality in all the supported environments | 1. Goto the Daraz App 2. Click on the ""Account"" button in the lower right corner 3.Click "setting" button at right upper corner 4.Click 'Account Information' page | None | Account Information' functionality should work in all the supported environments | Found as per the expectation |  | PASS

## Search
TS_R004
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCSE_001 | (TS_R004) Search Functionality | Verify searching with an existing Product Name | 1.Goto the Daraz App 2.Enter Any Existing Product on Search Box 3.Click Search button | Search Product Name : Samsung | Searched product should be displayed in the search results | Found as per the expectation | P2 | PASS
TCSE_002 | (TS_R004) Search Functionality | Verify searching with a non existing Product Name | 1.Goto the Daraz App 2.Enter Any Non Existing Product on Search Box 3.Click Search button | Search Product Name : Austkeyring | We cannot find any matches for your search term' should be displayed in the Search Results page' | Found as per the expectation | P2 | PASS
TCSE_003 | (TS_R004) Search Functionality | Verify searching without providing any Product Name | 1.Goto the Daraz App 2.Dont enter anything on Search box 3.Click Search button | None | Search Button should not work for empty search box | Found as per the expectation | P2 | PASS
TCSE_004 | (TS_R004) Search Functionality | Verifty searching for a product after login to the Application | 1.Goto the Daraz App 2.Login with your account 3.Enter Any Existing Product on Search Box 4.Click Search button | Search Product Name : Iphone | Searched product should be displayed in the search results | Found as per the expectation | P2 | PASS
TCSE_005 | (TS_R004) Search Functionality | Verify searching by providing a search criteria which results in mulitple products | 1.Goto the Daraz App 2.Enter multiple product name on Search Box 3.Click Search button | Search Product Name : Nokia Samsung | Searched multiple product should be displayed in the search results | Found as per the expectation | P2 | PASS
TCSE_006 | (TS_R004) Search Functionality | Verify search box placeholder | 1.Goto Daraz App 2.Click Search Icon | None | Search in Daraz' should be displayed as placeholder in searchbox | Found as per the expectation | P2 | PASS
TCSE_007 | (TS_R004) Search Functionality | Verify search history visibility | 1.Goto Daraz App 2.Enter any product 3.Click search button 4.Press back button 5.Press Search Box any see previvous product name down below | None | Search history Should be visible below the search box | Found as per the expectation | P2 | PASS
TCSE_008 | (TS_R004) Search Functionality | Verify previous search history visibility after logout | 1.Goto Daraz App 2.Logout Account 3.Click Search Box | None | Previous search history should not displayed in search history after logout | Found as per the expectation | P2 | PASS
TCSE_009 | (TS_R004) Search Functionality | Verify Search by selecting the category of product | 1.Goto Daraz App 2.Enter any valid catagory product on Search Box 3.Click Search button 4.Again goto Search Box 5.Enter any non valid catagory on Search Box 6.Click Search button | 1. Product is successfully displayed in the search results. 2. 'There is no product that matches the search criteria' is displayed in the Search Results page" | 1. Product should be successfully displayed in the search results. 2. 'We cannot find any matches for your search term' should be displayed in the Search Results page | Found as per the expectation | P2 | PASS
TCSE_010 | (TS_R004) Search Functionality | Verify the UI of Search functionality and Search page options | 1.Goto Daraz App 2.Click search icon | None | Proper UI adhering to the UI checklist should be displayed for the complete Search functionality | Found as per the expectation | P2 | PASS

## Add to Cart
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCAC_001 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from 'Product Display' Page | 1.Goto the Daraz App 2.Select any product 3.Click add to cart button | Search Product Name : Samsung | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_002 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Related Products section of the Product Display Page | 1.Goto the Daraz App 2.Select any product 3.Scroll Down and select Related Product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_003 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from Search Results Page | 1.Goto the Daraz App 2.Search any product 3.Select product 4.Click Add to Cart button | Search Product Name : Samsung | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_004 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Top picks for you' section of Home page | 1.Goto the Daraz App 2.Scroll down and Click 'Top Picks For You' 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_004 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Hot Deals'Sub section of Home page | 1.Goto the Daraz App 2.Scroll down and Click 'Hot Deals' 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_004 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Mega Deals' Sub section of Home page | 1.Goto the Daraz App 2.Scroll down and Click 'Mega Deal' 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_005 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Everyday Below section of Home page | 1.Goto the Daraz App 2.Scroll down and Click 'Everyday Below 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_005 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Trending Now' section of Home page | 1.Goto the Daraz App 2.Scroll down and Click 'Trending Now' 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_005 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the All Promotional section of Home page | 1.Goto the Daraz App 2.Scroll down and Click any Promotional section 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_005 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Free delivery' section of Home page | 1.Goto the Daraz App 2.Scroll down and 'Free Delivery' 3.Select a product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_006 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the category or sub-category page | 1.Goto the Daraz App 2.Search any catagory product 3.Select product 4.Click Add to Cart button | Select any product | 1. Success message with text - 'Added to cart successfully!' should be displayed 2. Product should be successfully displayed in the 'Shopping Cart' page | Found as per the expectation | P2 | PASS
TCAC_007 | (TS_R005) Add to Cart Functionality | Verify the UI of 'Add to Cart' funtionality | 1.Goto the Daraz App 2.Check the UI of the functioanality related to 'Add to Cart' | Select any product | Proper UI adhering to the UI checklist should be displayed for the 'Add to Cart' functionality | Found as per the expectation | P2 | PASS
TCAC_008 | (TS_R005) Add to Cart Functionality | Verify the 'Add to Cart' page functionality in all the supported environments | 1.Goto the Daraz App 2. Check the 'Add to Cart' functionality in all the supported environments | Select any product | 'Add to Cart' functionality should work correctly in all the supported environments | Found as per the expectation | P2 | PASS

## Home Page
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCH_001 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Shopping Cart' page | 1.Goto the Daraz App 2.Click"My Cart" button 3.Click back/home button | Search Product Name : Samsung | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_002 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Account page' | 1.Goto the Daraz App 2.Click "Account" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_003 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Message page' | 1.Goto the Daraz App 2.Click "Messages" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_004 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Discover page' | 1.Goto the Daraz App 2.Click "Discover" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_005 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Slide Bar' | 1.Goto the Daraz App 2.Click "Slide Bar" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_006 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from ''Any 3 for bdt 599" | 1.Goto the Daraz App 2.Click "Any 3 for bdt 599" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_007 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Categories' | 1.Goto the Daraz App 2.Click "Categories" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_008 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Daraz Coins' | 1.Goto the Daraz App 2.Click "Daraz Coins'" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_009 | (TS_R006) Home Page Functionality | Verify navigating to Home Page from 'Quick TopUP' | 1.Goto the Daraz App 2.Click "Quick Topup'" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_010 | (TS_R006) Home Page Functionality | Verify "Set your delivery location" field | 1.Goto the Daraz App 2.Click "Set your delivery location" field | None | 1.Field Should be clickable 2.Should Hover text"Set your delivery field" | 1.Found as per the expectation 2.Found as per the expectation | P2 | PASS
TCH_011 | (TS_R006) Home Page Functionality | Verify use my current location Automatically | 1.Goto the Daraz App 2.Click "Set your delivery location" field 3.Click "use my current location" 4.Give acces permission for GPS | None | User current location should be accessable automatically | Not Found as per expectation | P2 | FAIL
TCH_012 | (TS_R006) Home Page Functionality | Verify use my current location Manually if falid to acces user location | 1.Goto the Daraz App 2.Click "Set your delivery location" field 3.Click "use my current location" 4.Give acces permission for GPS 5.Select your area from dropdown section | None | User should can set location manually | Found as per the expectation | P2 | PASS
TCH_013 | (TS_R006) Home Page Functionality | Verify 'Scan QR' functionality | 1.Goto the Daraz App 2.Click QR logo from left top corner 3.Scan QR code | None | Should be accurately scan the QR Code | Found as per the expectation | P2 | PASS
TCH_014 | (TS_R006) Home Page Functionality | Verify "daraz 11" and promotion section can navigating to the product page | 1.Goto the Daraz App 2.Click daraz11 section | None | User should be taken to Product page | Found as per the expectation | P2 | PASS
TCH_015 | (TS_R006) Home Page Functionality | Verify "Any 3 for bdt 599" can navigating to the product page | 1.Goto the Daraz App 2.Click "Any 3 for bdt 599" section or "see more" button | None | User should be taken to Product page | Found as per the expectation | P2 | PASS
TCH_016 | (TS_R006) Home Page Functionality | Verify "catagories" and promotion section can navigatingto the product page | 1.Goto the Daraz App 2.Click"catagories" section | None | User should be taken to Product page | Found as per the expectation | P2 | PASS
TCH_017 | (TS_R006) Home Page Functionality | Verify "Just for you" and promotion section can navigatingto the product page | 1.Goto the Daraz App 2.Click "Just for you" section | None | User should be taken to Product page | Found as per the expectation | P2 | PASS
TCH_018 | (TS_R006) Home Page Functionality | Verify the UI of 'Home Page' funtionality | 1.Goto the Daraz App 2.Check the UI of the functioanality related to 'Home Page' | None | Proper UI adhering to the UI checklist should be displayed for the 'Home Page' functionality | Found as per the expectation | P2 | PASS
TCH_019 | (TS_R006) Home Page Functionality | Verify the Home page functionality in all the supported environments | 1.Goto the Daraz App 2. Check the Home page functionality in all the supported environments | None | 'Home Page" functionality should work correctly in all the supported environments | Found as per the expectation | P2 | PASS

## Check out
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCC_001 | (TS_R007) Check Out Functionality | Verify "New Add Address" Functionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address | Chose A product | User should be taken to Add New Address page | Found as per the expectation | P1 | PASS
TCC_002 | (TS_R007) Check Out Functionality | Verify navigating to Checkout page when there are no products added to the Shopping Cart | 1.Goto the Daraz App 2.Select no prduct 3.Click Add to Cart 4.Click Check out | None | User should be taken to an empty 'Shopping Cart' page instead of 'Checkout' page | Found as per the expectation | P1 | PASS
TCC_003 | (TS_R007) Check Out Functionality | Verify navigating to Checkout page using 'Shopping Cart' header option | 1.Goto the Daraz App 2.Click on checkout on header option | None | User should be taken to the checkout page | Found as per the expectation | P1 | PASS
TCC_004 | (TS_R007) Check Out Functionality | Verify entering random alphabet in add new address page full name field | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Full name | aabbfgs | Name Should not be accepted | Not Found as per the expectation | P1 | FAIL
TCC_005 | (TS_R007) Check Out Functionality | Verify entering Special character in add new address page full name field | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Full name | @@rafi | Should give a error message | Found as per the expectation | P1 | PASS
TCC_006 | (TS_R007) Check Out Functionality | Verify entering worng number in add new address page Mobile Number field | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Mobile Number 7.Press Save button | 391431455 | Should give a error message | Found as per the expectation | P1 | PASS
TCC_007 | (TS_R007) Check Out Functionality | Verify Area field in Add New Address page | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Mobile Number 7.Select your Area | Region: Dhaka City : Dhaka North Area : Adabor | Should succesfully select your area | Found as per the expectation | P1 | PASS
TCC_008 | (TS_R007) Check Out Functionality | Verify address field in Add New Address page with random number | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Mobile Number 7.Click your Area 8.Enter Random number in Address field | 0172924y435 | Should give a error message | Not Found as per the expectation | P1 | FAIL
TCC_009 | (TS_R007) Check Out Functionality | Verify address field in Add New Address page whether its hovering "Houne No / building /Area " Text | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click Add New Address 6.Enter Mobile Number 7.Click your Area 8.Check Address field | 0172924y435 | Should hover "Houne No / building /Area " Text | Found as per the expectation | P1 | PASS
TCC_010 | (TS_R007) Check Out Functionality | Checking "Default Delivery Address" sliderbar | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Default Delivery Address" slidebar | None | Should set delivery address by default | Found as per the expectation | P1 | PASS
TCC_011 | (TS_R007) Check Out Functionality | Checking "Default Billing Address" sliderbar | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Default Billing Address" slidebar | None | Should set billing address by default | Found as per the expectation | P1 | PASS
TCC_012 | (TS_R007) Check Out Functionality | Verifying "Store Voucher" functionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Store voucher" button | None | Should able to access voucher offer | Found as per the expectation | P1 | PASS
TCC_013 | (TS_R007) Check Out Functionality | Verifying "Store Vouchar" added sucessfully | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Store vouchar" button 6.Select a voucher | None | Should reduced price from actual price | Found as per the expectation | P1 | PASS
TCC_014 | (TS_R007) Check Out Functionality | Verifying "Use Daraz Coin" functionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Use Daraz Coin" button | None | Should show criteria "Daraz Club Member " Required | Found as per the expectation | P1 | PASS
TCC_015 | (TS_R007) Check Out Functionality | Verifying "Use Daraz Coin" functionality when you are Daraz Club Member | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Click "Use Daraz Coin" button | None | Should purchase using daraz club coin | Found as per the expectation | P1 | PASS
TCC_016 | (TS_R007) Check Out Functionality | Verifying "Order Summery" Calculation | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.check order summery | None | Calculation should be mathematically correct | Found as per the expectation | P1 | PASS
TCC_017 | (TS_R007) Check Out Functionality | Verifying Total Amount of bill hovering in footer section | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Fillout all field 6.Check Footer part | None | Total amount of bill should be visible | Found as per the expectation | P1 | PASS
TCC_018 | (TS_R007) Check Out Functionality | Verifying Total Amount of bill hovering in footer section | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Fillout all field 6.Check Footer part | None | Total amount of bill should be visible | Found as per the expectation | P1 | PASS
TCC_019 | (TS_R007) Check Out Functionality | Verifying "Place Order" button functionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Fillout all field 6.Click "Place Order" button | None | Should able to place order if every mandatory filled fillout correctly | Found as per the expectation | P1 | PASS
TCC_020 | (TS_R007) Check Out Functionality | Verifying "Place Order" button functionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Fillout all field 6.Click "Place Order" button | None | Should give error message if any mandatory filled misssing | Found as per the expectation | P1 | PASS
TCC_021 | (TS_R007) Check Out Functionality | Verify the UI of 'Check Out' funtionality | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5.Check the UI of the functioanality related to 'Check out Page' | None | Proper UI adhering to the UI checklist should be displayed for the 'Home Page' functionality | Found as per the expectation | P1 | PASS
TCC_022 | (TS_R007) Check Out Functionality | Verify the Home page functionality in all the supported environments | 1.Goto the Daraz App 2.Select a prduct 3.Click Add to Cart 4.Click Check out 5. Check the Home page functionality in all the supported environments | None | "Check out" functionality should work correctly in all the supported environments | Found as per the expectation | P1 | PASS

## Account
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCA_001 | (TS_R008) My Account Functionality | Verify navigating to 'My Account' page on login | 1.Goto the Daraz App 2.Click "My Account" 3.Click Login/Signup button | Select Previous logged account | User should be able to login and taken to 'My Account' page | Found as per the expectation | P3 | PASS
TCA_002 | (TS_R008) My Account Functionality | Verify navigating to 'My Account' page From cart page | 1.Goto the Daraz App 2.Click "Cart" 2.Click "My Account" | None | Should taken to 'My Account' page | Found as per the expectation | P3 | PASS
TCA_003 | (TS_R008) My Account Functionality | Verify all text visibility in "Account Page" | 1.Goto the Daraz App 2.Click "My Account" 3. Check all | None | Should all text are visible | Not Found as per expectation | P3 | FAIL
TCA_004 | (TS_R008) My Account Functionality | Verify navigating to 'Account' page From Message page | 1.Goto the Daraz App 2.Click "Message" 2.Click "My Account" | None | Should taken to 'Account' page | Found as per the expectation | P3 | PASS
TCA_005 | (TS_R008) My Account Functionality | Verify navigating to 'Account' page From Discover page | 1.Goto the Daraz App 2.Click "Discover" 2.Click "My Account" | None | Should taken to ' Account' page | Found as per the expectation | P3 | PASS
TCA_006 | (TS_R008) My Account Functionality | Verify navigating to ' Account' page From Home page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" | None | Should taken to 'Account' page | Found as per the expectation | P3 | PASS
TCA_007 | (TS_R008) My Account Functionality | Verify the UI of 'account page funtionality | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" | None | Proper UI adhering to the UI checklist should be displayed for the 'Account Page' functionality | Found as per the expectation | P3 | PASS
TCA_008 | (TS_R008) My Account Functionality | Verify the Account page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" | None | "Account" functionality should work correctly in all the supported environments | Found as per the expectation | P3 | PASS
TCA_008 | (TS_R008) My Account Functionality | Verify adding profile picture | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Select Profile Picture | None | Profile picture should be added | Found as per the expectation | P3 | PASS
TCA_009 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "My Oder" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click View All | None | Should taken to "My Order" Page | Found as per the expectation | P3 | PASS
TCA_010 | (TS_R008) My Account Functionality | Verify Fuctionalities "Account" page my order section | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Check my order section | None | All option should be workable | Found as per the expectation | P3 | PASS
TCA_011 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Coins" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click "Collect daily coin " | None | Should taken to "Daraz coin " Page | Found as per the expectation | P3 | PASS
TCA_012 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "My Messages " page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click my messages | None | Should taken to "My Messages" Page | Found as per the expectation | P3 | PASS
TCA_013 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Payment Options" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click Payment Options | None | Should taken to "Payment options" Page | Found as per the expectation | P3 | PASS
TCA_014 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Help Center" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click Help Center | None | Should taken to "Help Center" Page | Found as per the expectation | P3 | PASS
TCA_015 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Chat with US" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click Chat with Us | None | Should taken to "Chat with US" Page | Found as per the expectation | P3 | PASS
TCA_016 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "My reviews" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click My reviews | None | Should taken to "My reviews" Page | Found as per the expectation | P3 | PASS
TCA_017 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Influencer Hub" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click Influencer Hub | None | Should taken to "Influencer Hub" Page | Found as per the expectation | P3 | PASS
TCA_018 | (TS_R008) My Account Functionality | Verify navigating "Account" page to "Daraz candy" page | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click Daraz candy | None | Should taken to "Daraz candy" Page | Found as per the expectation | P3 | PASS

## My Order
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCMO_001 | (TS_R009) My Order Functionality | Verify navigating to 'My order' page from Account Page | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order | None | Should taken to 'My Order' page | Found as per the expectation | P2 | PASS
TCMO_002 | (TS_R009) My Order Functionality | Verify All order Section | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Check All Order | None | Should visible all order | Found as per the expectation | P2 | PASS
TCMO_003 | (TS_R009) My Order Functionality | Verify All order Section Buy again button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Check All Order 5.Click Buy Again | None | Should buy again product | Found as per the expectation | P2 | PASS
TCMO_004 | (TS_R009) My Order Functionality | Verify All order Section Pay now button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Check All Order 5.Click Buy Again | None | Should taken to 'Payment method' Page | Found as per the expectation | P2 | PASS
TCMO_005 | (TS_R009) My Order Functionality | Verify All order Section cancel button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Check All Order 5.Cleck Cancel button | None | Should cancel product from buying | Found as per the expectation | P2 | PASS
TCMO_006 | (TS_R009) My Order Functionality | Verify 'To Pay' section Buy again button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Pay 5.Click Buy Again | None | Should Buy again this product | Found as per the expectation | P2 | PASS
TCMO_007 | (TS_R009) My Order Functionality | Verify 'To Pay' section Pay now button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Pay 5.Click pay now | None | Should taken to 'Payment method' Page | Found as per the expectation | P2 | PASS
TCMO_008 | (TS_R009) My Order Functionality | Verify 'Cancel' section Pay now button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Pay 5.Click Cancel | None | Should cancel product from buying | Found as per the expectation | P2 | PASS
TCMO_009 | (TS_R009) My Order Functionality | Verify all necessary section visible | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order | None | Should visibel per item price, number of item , total amount , order date | Found as per the expectation | P2 | PASS
TCMO_010 | (TS_R009) My Order Functionality | Verify the UI of 'My order funtionality | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click My order | None | Proper UI adhering to the UI checklist should be displayed for the 'My order Page' functionality | Found as per the expectation | P2 | PASS
TCMO_011 | (TS_R009) My Order Functionality | Verify the My order page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click My Order | None | "My Order" functionality should work correctly in all the supported environments | Found as per the expectation | P2 | PASS
TCMO_012 | (TS_R009) My Order Functionality | Verify 'To Ship' section Buy again button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Ship 5.Click Buy Again | None | Should Buy again this product | Found as per the expectation | P2 | PASS
TCMO_013 | (TS_R009) My Order Functionality | Verify 'To Receive' section | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Received | None | Should visible previous all received product | Found as per the expectation | P2 | PASS

## Payment Method
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCPM_001 | (TS_R010) My Order Functionality | Verify navigating to 'Select Payment Method' page from My order Page | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now | None | Should taken to 'Select Payment Method' page | Found as per the expectation | P1 | PASS
TCPM_002 | (TS_R010) My Order Functionality | Verify navigating to 'Select Payment Method' page After Clicking 'Pay now' button | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now | None | Should taken to 'Select Payment Method' page | Found as per the expectation | P1 | PASS
TCPM_003 | (TS_R010) My Order Functionality | Verify navigating to 'Select Payment Method' page After Clicking 'Buy now' button | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now | None | Should taken to 'Select Payment Method' page | Found as per the expectation | P1 | PASS
TCPM_004 | (TS_R010) My Order Functionality | Verify 'Select Payment Method' have all userfriendly online payment method | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now 5.Check 'Select Payment Method' | None | Should have all payment option like bkash, Installment ,Credit Card/debit Card option , Rocket , Nagad , Dbbl Nexus Card | Found as per the expectation | P1 | PASS
TCPM_005 | (TS_R010) My Order Functionality | Verify 'Select Payment Method' have cash on delivery | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now 5.Check 'Select Payment Method' | None | Should have Cash on delivery method | Found as per the expectation | P1 | PASS
TCPM_006 | (TS_R010) My Order Functionality | Verify 'Select Payment Method' page all payment are accessable | 1.Goto the Daraz App 2.Click "My Account" 3.Select Product 4.Click Buy Now 5.Check 'Select Payment Method' | None | Should be accessable all payment options | Found as per the expectation | P1 | PASS
TCPM_007 | (TS_R009) My Order Functionality | Verify the UI of 'My order funtionality | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click My order | None | Proper UI adhering to the UI checklist should be displayed for the 'My order Page' functionality | Found as per the expectation | P1 | PASS
TCPM_008 | (TS_R009) My Order Functionality | Verify the My order page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "Home" 3.Click "My Account" 4.Click My Order | None | "My Order" functionality should work correctly in all the supported environments | Found as per the expectation | P1 | PASS
TCPM_009 | (TS_R009) My Order Functionality | Verify 'To Ship' section Buy again button | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Ship 5.Click Buy Again | None | Should Buy again this product | Found as per the expectation | P1 | PASS
TCPM_010 | (TS_R009) My Order Functionality | Verify 'To Receive' section | 1.Goto the Daraz App 2.Click "My Account" 3.Click My order 4.Click To Received | None | Should visible previous all received product | Found as per the expectation | P1 | PASS
TCPM_011 | (TS_R009) My Order Functionality | Verify 'Payment Options' section from my dervices section | 1.Goto the Daraz App 2.Click "My Account" 3.Click payment options | None | Should visible previous all possibel payment options | Not Found as per the expectation | P1 | FAIL

## My Return
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCMR_001 | (TS_R011) My Returns Functionality | Verify navigating to 'My Return' page from My Account Page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return | None | Should taken to 'My Return' page | Found as per the expectation |  | PASS
TCMR_002 | (TS_R011) My Returns Functionality | Verify submit the Product for return by filling all the fields and selecting all the options in the 'My Return' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return 4.Fill all the fields and select all the options in the 'My Returns' page | None | Should give return confimation mail to the user | Found as per the expectation |  | PASS
TCMR_003 | (TS_R011) My Returns Functionality | Verify clearing all the fields in the 'Product Returns' page and submit | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return 4.Fill all the fields and select all the options in the 'My Returns' page | None | Field level validation messages for all the mandatory fields in the 'Product Returns' page should be displayed and the request to submit the product return should not be processed | Found as per the expectation |  | PASS
TCMR_004 | (TS_R011) My Returns Functionality | Verify Placeholders for all the date and text fields in the 'Product Returns' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return | None | Proper placeholder text for all the date and text fields should be displayed | Found as per the expectation |  | PASS
TCMR_005 | (TS_R011) My Returns Functionality | Verify Back button on the 'my account' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return 4.Selcet backpress button | None | Should able to get back on My account page | Found as per the expectation |  | PASS
TCMR_006 | (TS_R011) My Returns Functionality | Verify E-Mail field in the 'My returns' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return 4.Verify Email | None | Field level validation messages for the E-Mail field should be displayed informing the user to provide valid email address | Found as per the expectation |  | PASS
TCMR_007 | (TS_R011) My Returns Functionality | Verify Order Date field in the 'My Returns' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return 4.Check all date | None | Field level validation messages for the 'Order Date' field should be displayed informing the user to provide the correct date. As this date cannot be in future. | Found as per the expectation |  | PASS
TCMR_008 | (TS_R011) My Returns Functionality | Verify the Page URL, Page Heading and Page Title of 'My Returns' page | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return | None | Correct Page URL, Page Heading and Page Title should be displayed in the 'Product Returns' page | Found as per the expectation |  | PASS
TCMR_009 | (TS_R011) My Returns Functionality | Verify the UI of 'Product Returns' page functionality | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return | None | Proper UI adhering to the UI checklist should be displayed for the 'My Returns' page functionality | Found as per the expectation |  | PASS
TCMR_010 | (TS_R011) My Returns Functionality | Verify the 'My Returns' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "My Account" 3.Select My Return | None | Check the 'My Returns' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Daraz live
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCDL_001 | (TS_R012) My Returns Functionality | Verify navigating to 'Daraz Live' page from My Account Page | 1.Goto the Daraz App 2.Click "Daral Live" | None | Should taken to 'Daraz Live' page | Found as per the expectation |  | PASS
TCDL_002 | (TS_R012) My Returns Functionality | Verify Daraz Live page Functionality | 1.Goto the Daraz App 2.Click "Daral Live" | None | Should display all live product | Not found as per the expectation |  | FAIL
TCDL_003 | (TS_R012) My Returns Functionality | Verify the UI of 'Daraz Live' page functionality | 1.Goto the Daraz App 2.Click "Daral Live" | None | Proper UI adhering to the UI checklist should be displayed for the 'Daraz Live' page functionality | Found as per the expectation |  | PASS
TCDL_004 | (TS_R012) My Returns Functionality | Verify the 'Daraz Live' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "Daral Live" | None | Check the 'Daraz Live' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Search Filter
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCSF_001 | (TS_R012) Search Filter Functionality | Verify navigating to 'Search Filter ' Sliderbar from Search Page | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product | fabrilife | Should open to 'search Filter' page | Found as per the expectation |  | PASS
TCSF_002 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' Button | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon | None | FIlter button should be workable | Found as per the expectation |  | PASS
TCSF_003 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar Promotion & Services section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click Promotion & Services | None | Should filter as select folllowing method | Found as per the expectation |  | PASS
TCSF_004 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar catagory section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click catagory | None | Should filter as select folllowing catagory | Found as per the expectation |  | PASS
TCSF_005 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar size section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click size button | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_006 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar Price section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Enter range price | 2000 | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_007 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar Rating section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click Rating button | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_008 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar Location button | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click location button | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_009 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar main material section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click main material | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_010 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar warranty type section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click warranty type | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_011 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar tee sleeve length section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.click tee sleeve length | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_012 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar clothing material section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.click clothing material | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_013 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar mens trend section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.click mens trend | None | Should filter as select folllowing brand | Found as per the expectation |  | PASS
TCSF_014 | (TS_R012) Search Filter Functionality | Verify 'Search Filter' slidebar Color family section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click family section | None | Should filter as select folllowing family section | Found as per the expectation |  | PASS
TCSF_015 | (TS_R012) Search Filter Functionality | Verify number of filtered item showing in section | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click some item | None | Should able to number of selected item | Found as per the expectation |  | PASS
TCSF_016 | (TS_R012) Search Filter Functionality | Verify apply button | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click some item 6.Click Apply button | None | Should filtered selected item and show product | Found as per the expectation |  | PASS
TCSF_017 | (TS_R012) Search Filter Functionality | Verify clear all button | 1.Goto the Daraz App 2.Click "Search box" 3.Search a Product 4.Click filter icon 5.Click some item 6.Click Clear all button | None | Should clear all selected filter | Found as per the expectation |  | PASS
TCSF_018 | (TS_R012) My Returns Functionality | Verify the UI of 'Daraz Live' page functionality | 1.Goto the Daraz App 2.Click "Daral Live" | None | Proper UI adhering to the UI checklist should be displayed for the 'Daraz Live' page functionality | Found as per the expectation |  | PASS
TCSF_019 | (TS_R012) My Returns Functionality | Verify the 'Daraz Live' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "Daral Live" | None | Check the 'Daraz Live' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Product Page
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCP_001 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Search Product | 1.Goto the Daraz App 2.Click "Search " box 3.Search any product 4.Select a product | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_002 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Top picks for you section on home page | 1.Goto the Daraz App 2.Click any product in top picks for you | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_003 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Any 3 for $699* Page | 1.Goto the Daraz App 2.Click any product in Any 3 for $699* | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_004 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Everyday Below Page | 1.Goto the Daraz App 2.Click Everyday Below Page 3.Click a product | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_005 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Catagory page | 1.Goto the Daraz App 2.Select a catagory | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_006 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Free delivery page | 1.Goto the Daraz App 2.Click Free delivery item | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_007 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Flash Sale Page | 1.Goto the Daraz App 2.Click Fash Sale section 3.Select a product | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_008 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from Tranding Now Page | 1.Goto the Daraz App 2.Click Tranding Now section 3.Select a product | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_009 | (TS_R012) Product Page Functionality | Verify navigating to 'Product Page' from just for 'Username' section on home page | 1.Goto the Daraz App 2.Click just for 'Username' section 3.Select a product | None | Should open to 'Product' page | Found as per the expectation |  | PASS
TCP_010 | (TS_R012) Product Page Functionality | Verify Product Page picture slider functionality | 1.Goto the Daraz App 2.Select a product 3.Check Slider bar | None | Should visible all product picture in slider | Found as per the expectation |  | PASS
TCP_011 | (TS_R012) Product Page Functionality | Verify Product Page Product name | 1.Goto the Daraz App 2.Select a product 3.Check Product name | None | Should same from where tou select the item | Found as per the expectation |  | PASS
TCP_012 | (TS_R012) Product Page Functionality | Verify Product Page Product Price Section | 1.Goto the Daraz App 2.Select a product 3.Check Product price | None | Should same as previous page price | Found as per the expectation |  | PASS
TCP_013 | (TS_R012) Product Page Functionality | Verify Product Page Product Price with discount | 1.Goto the Daraz App 2.Select a product 3.Check Product price | main price : 1,150 discount : 27% Actual Price : 839 | Should discount added properly with actual price | Found as per the expectation |  | PASS
TCP_014 | (TS_R012) Product Page Functionality | Verify rating Functionality | 1.Goto the Daraz App 2.Select a product 3.Check Rating | None | Should rating shown properly with toatal number of rating | Found as per the expectation |  | PASS
TCP_015 | (TS_R012) Product Page Functionality | Verify the number of toal sold and love product | 1.Goto the Daraz App 2.Select a product 3.Check total sold and toal love | None | Should the total number of product ssold and number of people love this product shown properly | Found as per the expectation |  | PASS
TCP_016 | (TS_R012) Product Page Functionality | Verify product delivery address and delivery price | 1.Goto the Daraz App 2.Select a product 3.Check delivery section | None | Should able to user location and delivery price | Found as per the expectation |  | PASS
TCP_017 | (TS_R012) Product Page Functionality | Verify serive section | 1.Goto the Daraz App 2.Select a product 3.Check service section | None | Should display service regarding this product | Found as per the expectation |  | PASS
TCP_018 | (TS_R012) Product Page Functionality | Verify ratiing & review section | 1.Goto the Daraz App 2.Select a product 3.Check rating review section | None | Should display user review and rating with product picture | Found as per the expectation |  | PASS
TCP_019 | (TS_R012) Product Page Functionality | Verify ask question functionality | 1.Goto the Daraz App 2.Select a product 3.Check ask question section | None | User should able to ask any question regarding this product | Found as per the expectation |  | PASS
TCP_020 | (TS_R012) Product Page Functionality | Verify Seller profile and store | 1.Goto the Daraz App 2.Select a product 3.Check seller profile section | None | Should display Seller name or store name with review and other | Found as per the expectation |  | PASS
TCP_021 | (TS_R012) Product Page Functionality | Verify highlight and description section | 1.Goto the Daraz App 2.Select a product 3.Check highlight and description section | None | Should properly document highlight and description section | Found as per the expectation |  | PASS
TCP_022 | (TS_R012) Product Page Functionality | Verify 'Buy Now' Button | 1.Goto the Daraz App 2.Select a product 3.Click Buy Now Button | None | Should Able to Buy this product | Found as per the expectation |  | PASS
TCP_023 | (TS_R012) Product Page Functionality | Verify 'Add to Cart' Button | 1.Goto the Daraz App 2.Select a product 3.Click Add to Cart Button | None | Should product added to cart succcessfully | Found as per the expectation |  | PASS
TCP_024 | (TS_R012) My Returns Functionality | Verify the UI of 'Product' page functionality | 1.Goto the Daraz App 2.Select a product | None | Proper UI adhering to the UI checklist should be displayed for the 'Product Page' page functionality | Found as per the expectation |  | PASS
TCP_025 | (TS_R012) My Returns Functionality | Verify the 'Product Page' page functionality in all the supported environments | 1.Goto the Daraz App 2.Select a product | None | Check the 'Product Page' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Cart
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCCA_001 | (TS_R012) Product Page Functionality | Verify navigating to 'Page Page' from Add to cart button | 1.Goto the Daraz App 2.Click "Search " box 3.Search any product 4.Select a product 5.Click Add to cart 6.Check cart page | None | Should able to add product cart page | Found as per the expectation |  | PASS
TCCA_002 | (TS_R012) Product Page Functionality | Verify cart page product | 1.Goto the Daraz App 2.Click cart icon | None | Should there see the product which you added to cart from product page | Found as per the expectation |  | PASS
TCCA_003 | (TS_R012) Product Page Functionality | Verify cart page Select to product functionality | 1.Goto the Daraz App 2.Click cart icon 3.Click product | None | User should click product which he want for checkout | Found as per the expectation |  | PASS
TCCA_004 | (TS_R012) Product Page Functionality | Verify Delete functionaolity on cat page | 1.Goto the Daraz App 2.Click cart icon 3.Delete a product from list | None | User should be able to remove any product from cart page | Found as per the expectation |  | PASS
TCCA_005 | (TS_R012) Product Page Functionality | Verify Vouchar functionality | 1.Goto the Daraz App 2.Click cart icon 3.Add vouchar code in vouchar field | DARAZ50 | User should successfully add vouchar | Found as per the expectation |  | PASS
TCCA_006 | (TS_R012) Product Page Functionality | Verify Vouchar Field with invalid Vouchar | 1.Goto the Daraz App 2.Click cart icon 3.Add vouchar code in vouchar field | daraz1111 | Should give a error message | Found as per the expectation |  | PASS
TCCA_007 | (TS_R012) Product Page Functionality | Verify total selected item amount | 1.Goto the Daraz App 2.Click cart icon 3.Select item | daraz1111 | Should item price additon functionality mathematically accurate | Found as per the expectation |  | PASS
TCCA_008 | (TS_R012) Product Page Functionality | Verify Checkout button | 1.Goto the Daraz App 2.Click cart icon 3.Select item | daraz1111 | Should open to check out page | Found as per the expectation |  | PASS
TCCA_009 | (TS_R012) Product Page Functionality | Verify the UI of 'Cart' page functionality | 1.Goto the Daraz App 2.Click cart icon | None | Proper UI adhering to the UI checklist should be displayed for the 'Cart Page' page functionality | Found as per the expectation |  | PASS
TCCA_010 | (TS_R012) Product Page Functionality | Verify the 'Cart Page' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click cart icon | None | Check the 'Cart Page' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Messages
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCME_001 | (TS_R013) Message Page Functionality | Verify navigating to 'Message Page' from Home Page | 1.Goto the Daraz App 2.Click "message" icon | None | Should open to Message page | Found as per the expectation |  | PASS
TCME_002 | (TS_R013) Message Page Functionality | Verify navigating to 'Message Page' from Discover Page | 1.Goto the Daraz App 2.Click "Discover" icon 3.Click "message" icon | None | Should open to Message page | Found as per the expectation |  | PASS
TCME_003 | (TS_R013) Message Page Functionality | Verify navigating to 'Message Page' from Cart Page | 1.Goto the Daraz App 2.Click "Cart" icon 3.Click "message" icon | None | Should open to Message page | Found as per the expectation |  | PASS
TCME_004 | (TS_R013) Message Page Functionality | Verify navigating to 'Message Page' from Account Page | 1.Goto the Daraz App 2.Click "Account" icon 3.Click "message" icon | None | Should open to Message page | Found as per the expectation |  | PASS
TCME_005 | (TS_R013) Message Page Functionality | Checking Chats button functionality | 1.Goto the Daraz App 2.Click "Messages" icon | None | Should open to Chats page | Found as per the expectation |  | PASS
TCME_006 | (TS_R013) Message Page Functionality | Checking Order button functionality | 1.Goto the Daraz App 2.Click "Messages" icon | None | Should open to Order page | Found as per the expectation |  | PASS
TCME_007 | (TS_R013) Message Page Functionality | Checking Notifications button functionality | 1.Goto the Daraz App 2.Click "Messages" icon | None | Should open to Notifications page | Found as per the expectation |  | PASS
TCME_008 | (TS_R013) Message Page Functionality | Checking Promos button functionality | 1.Goto the Daraz App 2.Click "Messages" icon | None | Should open to Promos page | Found as per the expectation |  | PASS
TCME_009 | (TS_R013) Message Page Functionality | Checking Notifications allow button | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click notification allert button | None | Should open device notification panel | Found as per the expectation |  | PASS
TCME_010 | (TS_R013) Message Page Functionality | Checking Notifications allow button | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click notification allert button | None | Should open device notification panel | Found as per the expectation |  | PASS
TCME_011 | (TS_R013) Message Page Functionality | Checking promotion slider in Messages page | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click notification allert button | None | Should able to slide every promos | Found as per the expectation |  | PASS
TCME_012 | (TS_R013) Message Page Functionality | Verify Chatbox field functionality | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click Chats 4.Click Shop name 5.Enter in Type your message box | Track | User should input chatbox | Found as per the expectation |  | PASS
TCME_013 | (TS_R013) Message Page Functionality | Verify Chatbox suggest chat functionaly | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click Chats 4.Click Shop name 5.Click a suggest chat | None | Suggest chat should be clickable | Found as per the expectation |  | PASS
TCME_014 | (TS_R013) Message Page Functionality | Verify Shop icon | 1.Goto the Daraz App 2.Click "Messages" icon 3.Click Chats 4.Click Shop name 5.Click shop icon from left upper corner | None | Should open shop page | Found as per the expectation |  | PASS
TCME_015 | (TS_R013) Message Page Functionality | Verify the UI of 'Messages' page functionality | 1.Goto the Daraz App 2.Click "message" icon | None | Proper UI adhering to the UI checklist should be displayed for the 'Messages' page functionality | Found as per the expectation |  | PASS
TCME_016 | (TS_R013) Message Page Functionality | Verify the 'Messages' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "message" icon | None | Check the 'Messages' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Discover
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCD_001 | (TS_R014) Discover Page Functionality | Verify navigating to 'Discover Page' from Home Page | 1.Goto the Daraz App 2.Click "Discover" icon | None | Should open to Discover page | Found as per the expectation |  | PASS
TCD_002 | (TS_R014) Discover Page Functionality | Verify navigating to 'Discover Page' from MessagesPage | 1.Goto the Daraz App 2.Click "message" icon 3.Click "Discover" icon | None | Should open to Discover page | Found as per the expectation |  | PASS
TCD_003 | (TS_R014) Discover Page Functionality | Verify navigating to 'Discover Page' from Cart Page | 1.Goto the Daraz App 2.Click "Cart" icon 3.Click "Discover" icon | None | Should open to Discover page | Found as per the expectation |  | PASS
TCD_004 | (TS_R014) Discover Page Functionality | Verify navigating to 'Discover Page' from AccountPage | 1.Goto the Daraz App 2.Click "Account" icon 3.Click "Discover" icon | None | Should open to Discover page | Found as per the expectation |  | PASS
TCD_005 | (TS_R013) Message Page Functionality | Checking "What can i help you find Today" textfield | 1.Goto the Daraz App 2.Click "Discover" icon 3.Enter product name | None | Should Input something | Found as per the expectation |  | PASS
TCD_006 | (TS_R013) Message Page Functionality | Checking Order button functionality | 1.Goto the Daraz App 2.Click "Messages" icon | None | Should open to Order page | Found as per the expectation |  | PASS
TCD_007 | (TS_R013) Message Page Functionality | Verify the UI of 'Discover' page functionality | 1.Goto the Daraz App 2.Click "message" icon | None | Proper UI adhering to the UI checklist should be displayed for the 'Discover' page functionality | Found as per the expectation |  | PASS
TCD_008 | (TS_R013) Message Page Functionality | Verify the 'Discover' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "message" icon | None | Check the 'Discover' page functionality in all the supported environments | Found as per the expectation |  | PASS

## Wishlist
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCW_001 | (TS_R015) Wish List Functionality | Verify Adding product to 'Wishlist' from Product Page | 1.Goto the Daraz App 2.Choose a product 3.Click Heart icon beside rating | None | Should added to wishlist | Found as per the expectation |  | PASS
TCW_002 | (TS_R015) Wish List Functionality | Verify Wishlist button fuctionality | 1.Goto the Daraz App 2.Choose a product 3.Click Heart icon beside rating | None | Button should be workable and after clicking button its color have to be changed | Found as per the expectation |  | PASS
TCW_003 | (TS_R015) Wish List Functionality | Verify navigating "My Wishlist" from Account Page | 1.Goto the Daraz App 2.Click account 3.Click my wishlist | None | Should open to my wishlist page | Found as per the expectation |  | PASS
TCW_004 | (TS_R015) Wish List Functionality | Verify Wishlist page product added to cart functionality | 1.Goto the Daraz App 2.Click account 3.Click my wishlist 4.Click Add to Cart button | None | Product should added to cart | Found as per the expectation |  | PASS
TCW_005 | (TS_R015) Wish List Functionality | Verify Wishlist page product delete functionality | 1.Goto the Daraz App 2.Click account 3.Click my wishlist 4.Click delete | None | Product should delete from wishlist | Found as per the expectation |  | PASS
TCW_006 | (TS_R015) Wish List Functionality | Verify ADD ALL TO CART button in wishlist page | 1.Goto the Daraz App 2.Click account 3.Click my wishlist 4.Click ass all to product | None | All product should successfully added to cart | Found as per the expectation |  | PASS
TCW_007 | (TS_R015) Wish List Functionality | Verify just for you functionality in wishlist page | 1.Goto the Daraz App 2.Click account 3.Check just for you segment | None | Recommended product list should be visible | Found as per the expectation |  | PASS
TCW_008 | (TS_R015) Wish List Functionality | Verify navigating "My Wishlist" to product page | 1.Goto the Daraz App 2.Click account 3.Click one product title from title | None | Should open to Product page | Found as per the expectation |  | PASS
TCW_009 | (TS_R013) Message Page Functionality | Verify the UI of 'Wish List' page functionality | 1.Goto the Daraz App 2.Click "message" icon | None | Proper UI adhering to the UI checklist should be displayed for the 'Wish List' page functionality | Found as per the expectation |  | PASS
TCW_010 | (TS_R013) Message Page Functionality | Verify the 'Wish List' page functionality in all the supported environments | 1.Goto the Daraz App 2.Click "message" icon | None | Check the 'Wish List' page functionality in all the supported environments | Found as per the expectation |  | PASS